GUIDANCE FOR PREPARING
EVENT HEALTH & MEDICAL PLANS

(EHMPs)

Ministry of Public Health - Republic of Lebanon

Content-Aligned Version 1.1 | July 2026

Document status: Non-binding implementation guidance supporting the National Protocol for Health and Medical Preparedness for Mass-Gathering Organized Sports or Recreational Events and Annexes A-D. The Protocol and Annex B define the mandatory requirements. This Guidance explains practical ways to meet them.

Evidence basis: The document is evidence-informed and includes numbered references to WHO, NAEMSP, AHA, World Athletics, UEFA, UKHSA and peer-reviewed mass-gathering medicine literature. Where Lebanon has adopted an administrative threshold or policy choice without a universally validated international cutoff, that distinction is stated explicitly.

# 1. Purpose and Use of this Guidance

This Guidance assists organizers, responsible organizer contacts, participating EMS and medical providers, Event Medical Directors, and Ministry reviewers in preparing and evaluating an Event Health & Medical Plan (EHMP). It translates the National Protocol and Annex B into a practical planning format. It does not create additional legal requirements. This Guidance applies only to events within the Protocol’s sports/recreational scope.

Use this Guidance to: structure an EHMP, identify essential operational details, prepare maps and contact lists, and confirm readiness before the event.

Use the National Protocol and Annex B to: determine what is mandatory for the assigned NEHRAT level.

Use Annex C to: submit and certify compliance for Level 2 and Level 3 events, and for Level 1 events when requested.

Use Annex D to: report post-event medical activity and significant incidents.

Core principle: The EHMP should be as short as possible while still allowing a person unfamiliar with the event to understand who is responsible, where resources are located, how help is requested, how a patient is reached and transported, and how the response escalates if the event exceeds normal capacity.

# 2. Planning Workflow

| Step | Action |
| --- | --- |
| 1 | Screen applicability under the National Protocol. |
| 2 | Complete NEHRAT (Annex A) and identify the final event level. |
| 3 | Review the applicable Annex B column. |
| 4 | Prepare the EHMP and supporting maps. |
| 5 | Obtain EMS readiness confirmation when required. |
| 6 | Submit Annex A for Level 1 notification. For Level 2 and Level 3, complete Annex C and submit the required package within the applicable timeline. |
| 7 | Brief teams, verify readiness and conduct the event. |
| 8 | Complete Annex D when required and use lessons for the next edition. |

# 3. Planning Depth by Event Level

| Planning element | Level 1 | Level 2 | Level 3 |
| --- | --- | --- | --- |
| Format | Brief written arrangements (usually 1 page) | Written EHMP | Comprehensive EHMP with maps and EMS declarations |
| Accountability & Medical leadership | Responsible organizer contact | Responsible organizer contact and participating-provider operational contacts. | Licensed physician Event Medical Director and participating-provider operational contacts |
| Medical teams | Trained first-aid personnel | BLS team(s) operating under the participating provider’s protocols and organizational oversight | Integrated medical and BLS teams under event medical command |
| Medical treatment post | Not required | Recommended | Required |
| Ambulance/EMS | Access to local EMS | Defined in EHMP | EMS resources documented and coordinated |
| Major-incident plan | Emergency escalation procedure | Written plan | Detailed coordinated plan |
| Submission to MOPH | Annex A notification; full package only if requested | At least 14 calendar days | At least 30 calendar days |

Proportionality: Do not turn a Level 1 arrangement into a lengthy manual. Do not reduce a Level 3 plan to a list of tents and ambulances. The depth of planning should match the assigned event level and the complexity of the site, route, crowd and response system.

# 4. Recommended EHMP Structure

Use the following sequence. Sections may be combined where this improves clarity, but none of the applicable content should be omitted.

| Section | Minimum content | Primary owner |
| --- | --- | --- |
| 1. Document control | Plan title, event, version, date, author, Organizer approval, Event Medical Director approval for Level 3 | Organizer |
| 2. Event profile | Location/route, schedule, peak attendance, participants, spectators, staff | Organizer |
| 3. Risk summary | Final NEHRAT level, key hazards, previous incidents, local constraints | Organizer + participating medical/EMS provider; Event Medical Director for Level 3 |
| 4. Accountability, provider contacts, and Level 3 medical direction | Organizer contact, participating-provider operational contacts, and Event Medical Director and command arrangements for Level 3 | Organizer/ Event Medical Director |
| 5. Staffing and deployment | Numbers, roles, shifts, locations, competencies and relief | Medical leadership + EMS |
| 6. Treatment post(s) | Location, staffing, equipment, patient flow and access | Organizer + medical leadership |
| 7. CPR and AED response | Recognition, EMS activation, CPR, AED access, handover and drills | Medical leadership |
| 8. Patient access/extraction | Routes, gates, loading points, barriers and responsible teams | Organizer + EMS |
| 9. Ambulance and hospital plan | Units, dispatch, destinations, continuity and escalation | EMS + medical leadership |
| 10. Coordination and communications; medical command for Level 3 | Command structure, channels, call signs, backups and briefing | Medical leadership |
| 11. Major incident/MCI plan | Activation, triage, casualty collection, loading, hospitals and escalation | Event Medical Director + EMS |
| 12. Contingencies | Weather, crowd, venue and activity-specific response triggers | Organizer + medical leadership |
| 13. Patient records and reporting | Care documentation, confidentiality, transfers and Annex D | Medical leadership |
| 14. Maps and directories | Site/deployment map, extraction routes, contact directory | Organizer |

# 5. Preparing Each EHMP Section

## 5.1 Document Control and Event Profile

Use one document title and version number throughout the submission.

Identify the organizer’s legal name and the person authorized to make operational decisions.

Record event dates, public opening/closing times, setup and demobilization periods, and the time medical coverage begins and ends.

State the maximum simultaneous attendance used in NEHRAT and separate participants, spectators, staff, performers, contractors and volunteers.

Identify all venues, route segments and municipalities covered by the plan.

## 5.2 Risk Summary

Copy the final NEHRAT score and event level; do not create a second classification system inside the EHMP.

List the main medical hazards that affect deployment, such as physical exertion, crowd movement, environmental exposure, difficult extraction, alcohol availability, water, height, speed or previous serious incidents.

Summarize relevant medical activity from previous editions, including hospital transports, cardiac arrests, deaths, unplanned resource requests and major incidents.

Identify local constraints, including limited ambulance availability, long transport time, road closures or receiving-hospital limitations.

Mass-gathering guidance consistently supports planning that considers event type, crowd size and behavior, duration, environment, venue, access, local system capacity and prior event data rather than relying on attendance alone. [1-6]

## 5.3 Accountability, Provider Contacts and Level 3 Medical Direction

Level 1: Identify the responsible organizer contact and the person responsible for activating EMS.

Level 2: Identify the responsible organizer contact and the operational contact of each participating emergency medical service or medical provider. Define deployment responsibilities, communications, escalation pathways, and interfaces with event control, security, and public emergency services.

Each participating provider remains responsible for its personnel, qualifications, authorization, equipment, protocols, clinical practice, patient care, documentation, and organizational oversight.

Level 3: Identify the licensed physician Event Medical Director, the medical-command location, reporting relationships, decision authority, deputy arrangements, and integration with participating emergency medical service and medical providers.

Use an operational coordination diagram for Level 2 and a medical-command structure for Level 3.

## 5.4 Staffing and Deployment

Provide a roster or staffing table showing role, qualification, team, location, shift start/end and contact method.

Deploy teams according to the event map, expected patient locations and extraction constraints—not only at the main entrance or finish line.

Ensure relief, hydration, weather protection and rest for long events.

Use the same role titles and call signs in the EHMP, maps, radio plan and briefing.

Do not assume that one universal staff-to-attendee ratio is valid for every event. Use Annex B, NEHRAT, previous event activity, event-specific hazards, route/site coverage, transport time, and local EMS capacity to justify the plan. [4-9]

Practical standard: The EHMP should explain why the proposed resources are sufficient. A list of staff and vehicles without deployment, communication and escalation arrangements is not a complete medical plan.

## 5.5 Medical Treatment Post(s)

Level 2: a treatment post is recommended when patient volume, weather, privacy, observation needs or transport delays justify it.

Level 3: at least one medical treatment post is required; additional posts may be needed for large, multi-zone or route events.

Identify location, opening time, staff, capacity, equipment, communication method and ambulance access.

Provide shelter, lighting, privacy, safe access, hand hygiene, waste disposal, sharps management where relevant, and a clear patient entry/exit flow.

Separate routine first aid from resuscitation and ambulance loading where feasible.

## 5.6 Medical Equipment, Supplies and Medicines

List equipment by location or team and identify who checks it before opening.

Include basic first-aid supplies, PPE, communication equipment and documentation materials at all applicable levels.

For Level 2 and Level 3, the EHMP should identify oxygen, AED capability, and airway/resuscitation equipment appropriate to the assigned personnel, scope of practice, event risks, and Annex B requirements.

Medicines may be carried or administered only by professionals authorized to do so under applicable Lebanese requirements and the medical governance of the event.

Include a process for replacing used, expired or failed equipment during the event.

Sport governing bodies such as UEFA and World Athletics use pre-event equipment and medical-room requirements to support reliable response; these examples should inform, but not automatically replace, the Lebanese event-specific plan. [10-12]

## 5.7 Cardiac Arrest, CPR and AED Response

Define how a collapse is recognized, reported and located.

Define who starts high-quality CPR, who brings the AED, who activates EMS and who directs the resuscitation until handover.

Show AED locations and responder deployment on the medical map.

Plan for crowd access, locked doors, stairs, route distance and communication delays.

Ensure pads, batteries and equipment are checked before opening and after use.

For Level 3, a brief pre-event test or drill of the cardiac-arrest response pathway is recommended.

Evidence-informed performance target: Plan AED placement and responder deployment to support immediate CPR and defibrillation as early as possible. Effective AED programs aim for shock delivery within about 3-5 minutes of collapse; the AHA advises site planning so an AED can be retrieved and returned within approximately 3-5 minutes. [13-14]

## 5.8 Patient Access and Extraction

Mark every ambulance-access point, extraction route, gate, stair, lift, water access point and route obstruction on the map.

Assign responsibility for keeping routes open and unlocking gates.

Describe the method used where an ambulance cannot directly reach a patient: stretcher team, cart, rescue vehicle, water rescue, rope rescue or other trained capability.

Confirm night lighting and bad-weather access where applicable.

Plan separate routes for incoming emergency resources and outgoing ambulances where congestion is likely.

## 5.9 Ambulance, EMS and Receiving-Hospital Arrangements

Name each participating EMS agency and its operational contact.

State the number and type of committed units, deployment locations, hours of coverage and dispatch method.

Define how event coverage is maintained when an ambulance transports a patient.

Identify the primary and alternate receiving emergency departments, expected travel time, contact method and any relevant capability limitations.

For Level 3, include the signed EMS Readiness Declaration from each participating EMS agency and ensure the agency’s role matches the EHMP and deployment map.

Describe how additional EMS resources are requested if planned capacity is exceeded.

## 5.10 Coordination, Medical Command and Communications

Identify the responsible organizer contact and operational contacts of participating providers.

Provide primary and backup communication methods and define how medical and EMS teams communicate with event control, security, EMS dispatch, and receiving hospitals.

For Level 3 events, identify the Event Medical Director, medical-command location, command relationships, and communication pathways.

Use plain language for critical messages and confirm that all teams understand the escalation terminology.

Include a plan for radio failure, mobile network failure or overloaded communications.

## 5.11 Major-Incident and Mass-Casualty Plan

Level 2 and Level 3 EHMPs must contain a written major-incident and mass-casualty plan. The plan should be concise and operational, not a generic copy of another organization’s disaster plan.

Activation criteria and who may declare or recommend a major incident.

Medical command and integration with the overall incident command structure.

The single triage method to be used by all participating teams.

Casualty collection and treatment areas, ambulance loading points and access routes.

Procedure for requesting additional EMS, hospital, Civil Defence, security and other public resources.

Receiving-hospital notification and patient distribution.

Maintenance of routine event medical coverage while the incident is managed.

Authority and communication pathway for event suspension, evacuation or termination.

Patient identification, tracking and family/reunification arrangements where applicable.

A process for staff safety, debriefing and after-action review.

Minimum test: A reviewer should be able to answer: Who declares the incident? Who commands medical operations? Where are casualties moved? How are ambulances loaded? Which hospitals receive patients? How are more resources requested?

## 5.12 Environmental and Event-Specific Contingencies

Identify objective triggers for heat, cold, lightning, wind, snow, air quality, flooding or other relevant conditions.

Identify the organizer representative authorized to modify, delay, pause, evacuate, or cancel the event and the medical or EMS personnel authorized to provide professional advice within their scope.

For Level 3 events, identify the Event Medical Director’s authority to recommend interruption, evacuation, or termination for medical reasons.

Describe the action linked to each trigger: extra water, cooling, warming, route modification, shelter, delayed start, suspension or evacuation.

Include event-specific risks such as crowd compression, intoxication, contact injury, water rescue, remote terrain, speed, fire or animal-related injury.

Avoid duplicating security or fire plans; instead, state how medical operations integrate with them.

## 5.13 Patient Care Documentation and Confidentiality

Document every patient assessed or treated using a consistent record.

At minimum record date/time, patient identifier, age or age group, complaint/injury, assessment, treatment, disposition, transport destination and provider.

Document refusal of care or transport using the provider’s approved process.

Protect patient information and limit access to authorized personnel.

Ensure aggregate totals can be transferred accurately to Annex D without disclosing unnecessary personal information.

## 5.14 Readiness, Briefing and Demobilization

Before opening, verify staff attendance, posts, equipment, AEDs, oxygen, radios, routes, ambulances, hospitals, weather and major-incident roles.

Conduct a short multidisciplinary briefing using the same map and contact directory.

For Level 3, test communication between medical command and EMS and confirm the cardiac-arrest and major-incident pathways.

Maintain coverage until the risk period ends, including audience departure and participant recovery where applicable.

After the event, collect records, restock equipment, identify significant issues and complete Annex D when required.

# 6. Event-Type Planning Considerations

| Event type | Common planning concerns | EHMP emphasis |
| --- | --- | --- |
| Indoor seated conference or exhibition | Large building, multiple floors, older attendees, long sessions | Emergency access, internal wayfinding, first-aid contact, AED location, lift/stair extraction |
| Concert, festival or nightclub | Standing crowd, movement, heat, noise, intoxication, access obstruction | Sector coverage, visible medical access, crowd-to-medical communication, extraction, surge capacity |
| Team sport or stadium event | Participant injuries plus spectator illness; rivalry and crowd separation | Separate player/spectator pathways, pitch/court access, treatment room/post, ambulance egress |
| Running, cycling or endurance event | Long route, exertion, environment, dispersed patients, finish-line surge | Course sectors, mobile teams, extraction, communications, finish medical area, sweep/closure plan |
| Combat sport | Head/neck injury, rapid deterioration, ringside decisions | Physician authority, immediate resuscitation, direct ambulance access, receiving hospital |
| Open-water event | Drowning, hypothermia/heat, difficult location, water extraction | Water rescue integration, recovery points, CPR/AED at exit, transport and hospital plan |
| Mountain, trail or winter event | Remote terrain, weather, poor communication, delayed extraction | Rescue capability, location tracking, weather triggers, warming, alternate routes and evacuation |
| Motorsport | High-energy trauma, fire, entrapment, course access | Fire/rescue integration, extrication, trauma destination, track control and dedicated access |
| School or university special event | Minors, guardianship, school staff, varied medical needs | Guardian contact, pediatric supplies where appropriate, child safeguarding and reunification |

# 7. EHMP Submission Package

Submission should follow the assigned event level. Files should use consistent event names and version numbers.

Level 1: submit Annex A as event notification before final event authorization, or at least seven calendar days before the event where no external authorization is required.

Level 2: submit Annex A, Annex C, the EHMP, and the event site or route map at least fourteen calendar days before the event.

Level 3: submit Annex A, Annex C, the comprehensive EHMP, the site or route map, the medical deployment map, and an EMS Readiness Declaration from each participating EMS agency at least thirty calendar days before the event.

A Level 1 organizer submits Annex C and a full EHMP only when requested by MOPH or another competent authority.

All submissions should include any additional supporting documentation requested by MOPH.

A material change requires an updated version and resubmission as directed by the National Protocol.

Version control: When a material change occurs, update the EHMP version number and date, clearly identify the change, and ensure all organizers, medical leaders and EMS agencies are working from the same approved version.

# 8. One-Page Pre-Opening Readiness Check

Use only the checks applicable to the assigned event level and the approved or submitted EHMP.

| Check | Confirmed |
| --- | --- |
| Final attendance, schedule, weather and route reviewed | ☐ |
| Responsible organizer contact and participating-provider operational contacts present and contactable; Event Medical Director present and contactable for Level 3 | ☐ |
| All planned staff and teams present | ☐ |
| Treatment post(s) open and equipped | ☐ |
| AEDs, oxygen and resuscitation equipment checked | ☐ |
| Ambulances and EMS contacts confirmed | ☐ |
| Patient extraction and emergency access routes open | ☐ |
| Receiving hospital contacts confirmed | ☐ |
| Primary and backup communications tested | ☐ |
| Cardiac-arrest roles briefed | ☐ |
| Major-incident roles and locations briefed | ☐ |
| Patient documentation available | ☐ |
| Event control/security know how to activate medical response | ☐ |

# 9. Post-Event Review and Data Use

Complete Annex D within seven calendar days after every Level 3 event, after a reportable event at Level 1 or Level 2, or when requested by MOPH. Notify MOPH of a cardiac arrest, death, major incident, or interruption or termination for medical reasons as soon as practicable and no later than twenty-four hours after the occurrence.

Review all hospital transports, cardiac arrests, deaths, major incidents, unplanned resource requests and interruptions for medical reasons.

Compare actual demand with the EHMP assumptions and identify changes required for the next edition.

Use previous event data in future NEHRAT Domain 9 scoring and resource planning.

Optional planning metrics: Patient Presentation Rate (PPR) = patients assessed or treated ÷ attendance × 1,000. Transport-to-Hospital Rate (TTHR) = hospital transports ÷ attendance × 1,000. These metrics support comparison across editions but should not replace clinical and operational review. [5-8]

# Appendix 1 - EHMP Template

Organizers may use this template or another format that addresses all applicable Protocol and Annex B requirements.

## A. Document Control

| Event name |  |
| --- | --- |
| EHMP version/date |  |
| Prepared by |  |
| Event Medical Director — Level 3 |  |
| Organizer approval |  |
| Final NEHRAT level |  |

## B. Event Profile

| Date(s) and operating hours |  |
| --- | --- |
| Venue/route and municipality |  |
| Maximum simultaneous attendance |  |
| Participants/competitors |  |
| Spectators/attendees |  |
| Staff/performers/volunteers |  |
| Event activity and schedule |  |
| Previous editions and significant medical history |  |

## C. Accountability, Provider Contacts and Level 3 Medical Direction

| Role | Name | Organization | Telephone | Radio/call sign |
| --- | --- | --- | --- | --- |
| Organizer contact |  |  |  |  |
| Event Medical Director Level 3 |  |  |  |  |
| Deputy Event Medical Director — Level 3, where appointed |  |  |  |  |
| EMS operational lead |  |  |  |  |
| Event control/security lead |  |  |  |  |
| Primary receiving ED |  |  |  |  |
| Alternate receiving ED |  |  |  |  |

## D. Medical Resources and Deployment

| Resource/team | Number | Location | Hours | Lead/contact | Notes |
| --- | --- | --- | --- | --- | --- |

## E. Operational Arrangements

| Required section | Plan summary / document reference |
| --- | --- |
| Treatment post(s) |  |
| Equipment and medicines |  |
| CPR and AED response |  |
| Patient access and extraction |  |
| Ambulance and transport arrangements |  |
| Receiving hospitals |  |
| Medical command and communications |  |
| Major-incident/MCI plan |  |
| Environmental contingencies |  |
| Patient documentation and reporting |  |
| Continuity of coverage and demobilization |  |

## F. Required Attachments

Site/route map

Medical deployment map

Contact directory

EMS Readiness Declaration(s), Level 3

Any additional MOPH-requested documentation

# Appendix 2 - Map and Communication Standards

## Minimum Map Labels

Event boundary, route and sector names.

Public entrances/exits and emergency gates.

Medical treatment posts and first-aid points.

Medical response team locations.

AED locations.

Ambulance deployment and loading points.

Patient extraction routes and barriers.

Medical command and event control locations.

Casualty collection area(s) for a major incident.

Primary and alternate evacuation routes.

## Minimum Communication Directory

| Function | Primary contact | Backup contact | Method/channel |
| --- | --- | --- | --- |
| Organizer |  |  |  |
| Medical command |  |  |  |
| EMS dispatch/lead |  |  |  |
| Security/event control |  |  |  |
| Civil Defence (if applicable) |  |  |  |
| Primary hospital |  |  |  |
| Alternate hospital |  |  |  |
| MOPH contact |  |  |  |

# 10. Evidence Basis

This Guidance is evidence-informed. Its planning principles are drawn from international public-health and event-medicine guidance, professional position statements, sports medical standards and peer-reviewed research. The mandatory Lebanese requirements remain those in the National Protocol and Annex B.

Important distinction: International sources support the use of risk assessment, proportional medical planning, medical leadership, command and communications, access and transport planning, CPR/AED readiness, major-incident planning, and post-event review. They do not validate every exact Lebanese threshold or level boundary. Attendance bands, submission timelines and minimum-level designations are national administrative standards adopted for implementation and should be evaluated through pilot use and national data.

| Guidance topic | Principal supporting references |
| --- | --- |
| Risk assessment and all-hazards planning | WHO [1-3]; WHO EMRO [4]; NAEMSP [5-6] |
| Proportional resource planning and use of historical data | NAEMSP [5-6]; Arbon [7-8]; UKHSA [9] |
| Road-race and sport-event medical organization | World Athletics [10-11]; UEFA [12] |
| CPR, early defibrillation and AED program design | AHA 2025 Guidelines [13]; AHA AED Guide [14] |
| Simulation, readiness testing and after-action learning | WHO simulation guide [3]; WHO EMRO [4] |

Document maintenance: MOPH should update examples, templates and references as national experience grows. Changes to this non-binding Guidance do not require amendment of the Protocol unless the policy itself changes.

# 11. References

1. World Health Organization. Public health for mass gatherings: key considerations. 2015. https://www.who.int/publications/i/item/public-health-for-mass-gatherings-key-considerations

2. World Health Organization. The generic all-hazards risk assessment and planning tool for mass gathering events. 2023. https://www.who.int/publications/i/item/WHO-2023-Generic-Mass-gatherings-All-Hazards-RAtool-2023-1

3. World Health Organization. Mass gathering practical guide for simulation exercises and after-action reviews. 2025. https://www.who.int/publications/i/item/9789240104846

4. WHO Regional Office for the Eastern Mediterranean. Framework for strengthening public health readiness for mass gatherings in the Eastern Mediterranean Region, 2023-2028. 2023. https://applications.emro.who.int/docs/WHOEMIHR020E-eng.pdf

5. Margolis AM, Leung AK, Friedman MS, McMullen SP, Guyette FX, Woltman N. Position Statement: Mass Gathering Medical Care. Prehospital Emergency Care. 2021;25(4):593-595. doi:10.1080/10903127.2021.1903632. https://pubmed.ncbi.nlm.nih.gov/33886431/

6. Schwartz B, Nafziger S, Milsten A, Luk J, Yancey A. Mass Gathering Medical Care: Resource Document for the National Association of EMS Physicians Position Statement. Prehospital Emergency Care. 2015;19(4):559-568. doi:10.3109/10903127.2015.1051680. https://doi.org/10.3109/10903127.2015.1051680

7. Arbon P, Bridgewater FHG, Smith C. Mass gathering medicine: a predictive model for patient presentation and transport rates. Prehospital and Disaster Medicine. 2001;16(3):150-158. doi:10.1017/S1049023X00025905. https://pubmed.ncbi.nlm.nih.gov/11875799/

8. Arbon P. The development of conceptual models for mass-gathering health. Prehospital and Disaster Medicine. 2004;19(3):208-212. doi:10.1017/S1049023X00001795. https://pubmed.ncbi.nlm.nih.gov/15571196/

9. UK Health Security Agency. Healthcare provision at events: a rapid scoping review. 2026. https://www.gov.uk/government/publications/healthcare-provision-at-events-a-rapid-scoping-review

10. World Athletics. Competition Medical Guidelines for World Athletics Series Events. Second edition. 2020. https://worldathletics.org/download/download?filename=a20d107f-c682-48be-8c54-b4c3764de329.pdf&urlslug=World+Athletics+Competition+Medical+Guidelines+-+October+2020+Second+Edition

11. World Athletics. Label Road Race Regulations. 2025. https://worldathletics.org/download/download?filename=dca459ef-f1d6-4415-a647-df9188d4b7a1.pdf&urlslug=C1.6+-+Label+Road+Race+Regulations

12. Union of European Football Associations. UEFA Medical Regulations. 2025 online edition. https://documents.uefa.com/r/Technical-Regulations/UEFA-Medical-Regulations-Online

13. American Heart Association. 2025 Guidelines for Cardiopulmonary Resuscitation and Emergency Cardiovascular Care. 2025. https://cpr.heart.org/en/resuscitation-science/cpr-and-ecc-guidelines

14. American Heart Association. Your On-site AED Program: An Implementation Guide. Updated 2023. https://cpr.heart.org/-/media/CPR-Files/Training-Programs/AED-Implementation/2023-updates/KJ1683-AED-Guide.pdf